## README
This workbook was originally linked to company_X_demand.xlsx. They were originally uploaded to a Sharepoint site.
The purpose was for shipments_planning.xlsx to be updated by two outside entitites, that is, the origin agent in country A, plus the destination agent in country B.
Therefore, ultimately, number of containers are determined by number of POs entered, separated by commas.
All data has been altered.

## Container Bookings
Week | Number of containers | Planned Loading date | Changed Loading Date | PO | Their Load# | Booking # | Container # | Vessel | ETD | ETA
28 | 2 | 2020-07-10 |  | 134, 136 | 12345 | 175828 | CAIU8339728, HLXU8377651 | OOCL Montreal 29W29 | 2020-07-16 | 2020-07-28
29 | 1 | 2020-07-17 |  | 137 | 12346 | 175829 | HAMU1179894 | Toronto Express 23W30 | 2020-07-23 | 2020-08-04
30 |  | 2020-07-24
31 | 1 | 2020-07-31 |  | 138139 | 123457 | 175830 | MRKU4660109, MRKU5269070 | EM KEA 032W | 2020-08-03 | 2020-08-17
32 |  | 2020-08-07 |  |  | 123458 | 175831 |  | OTTAWA EXPRESS 14W33 | 2020-08-13 | 2020-08-28
33 | 1 | 2020-08-14 |  | 143 | 123459 | 175832 | OOCU6547995 | TORONTO EXPRESS 24W34 | 2020-08-20 | 2020-09-01
34 | 2 | 2020-08-21 |  | 144, 149 | 123460 | 175833 | UETU5366397, OOLU8485841 | MONTREAL EXPRESS 20W35 | 2020-08-27 | 2020-09-08
35 | 2 | 2020-08-28 |  | 150, 157 | 123461 | 175834 | OOCU7148829, FCIU9512667 | GERHARD SCHULTE 001 W | 2020-09-03 | 2020-09-15
36 | 1 | 2020-09-04 |  | 158 | 123462 | 175835 | OOLU9402369 | OOCL MONTREAL 31W37 | 2020-09-10 | 2020-09-22
37 | 1 | 2020-09-11 |  | 159 | 123463 | 175836 | UETU5461373 | TORONTO EXPRESS 25W38 | 2020-09-17 | 2020-09-29
38 | 1 | 2020-09-18 |  | 162 | 123464 | 175837 | FSCU 8239006 | MONTREAL EXPRESS 21W39 | 2020-09-24 | 2020-10-06
39 | 1 | 2020-09-25 |  | 163 | 123465 | 175838 | HLBU3427705 | GERHARD SCHULTE 02W40 | 2020-10-01 | 2020-10-13
40 | 2 | 2020-10-02 |  | 164, 165 | 123466 | 175839 | HLBU3408325, UACU6053685 | OOCL MONTREAL 32W41 | 2020-10-08 | 2020-10-20
41 | 1 | 2020-10-09 |  | 167 | 123467 | 175840 | TCNU6745188 | TORONTO EXPRESS 26W42 | 2020-10-15 | 2020-10-27
42 | 1 | 2020-10-16 |  | 168 | 123468 | 175841 | HLXU8622954 | MONTREAL EXPRESS 22W43 | 2020-10-22 | 2020-11-03
43 | 1 | 2020-10-23 |  | 173 | 123469 | 175842 | HLBU3421590 | QUEBEC EXPRESS 59W44 | 2020-10-29 | 2020-11-10
44 | 1 | 2020-10-30 |  | 174 | 123470 | 175843 | HLBU1443353 | OOCL MONTREAL 33W45 | 2020-11-05 | 2020-11-17
45 | 1 | 2020-11-06 |  | 180 | 123471 | 175844 | HASU4084855 | MAERSK PALERMO | 2020-11-12 | 2020-11-23
45 | 1 | 2020-11-06 |  | 179 | 123472 | 175845 | HLBU2699252 | TORONTO EXPRESS 27W46 | 2020-11-12 | 2020-11-24
46 | 1 | 2020-11-13 |  | 181 | 123473 | 175846 | SKYU8037950 | MONTREAL EXPRESS 23W47 | 2020-11-23 | 2020-12-01
47 | 2 | 2020-11-20 |  | 197, 200 | 123474 | 175847 | BMOU6697126, HLBU3146375 | QUEBEC EXPRESS 60W48 | 2020-11-28 | 2020-12-08
48 | 1 | 2020-11-27 |  | 182 | 123475 | 175848 | BSIU9855616 | OOCL MONTREAL 34W49 | 2020-12-03 | 2020-12-15
49 | 2 | 2020-12-04 |  | 201, 202 | 123476 | 175849 | HAMU1313494, HLBU1061788 | TORONTO EXPRESS 28W50 | 2020-12-13 | 2020-12-23
50 | 2 | 2020-12-11 |  | 206, 207 | 123477 | 175850 | BEAU4716876, UACU8585856 | MONTREAL EXPRESS 24W51 | 2020-12-20 | 2021-01-05
51 | 2 | 2020-12-18 |  | 208, 209 | 123478 | 175851 | CAIU4262130, TCLU4148170 | QUEBEC EXPRESS 61W52 | 2020-12-24 | 2021-01-05
52 |  | 2020-12-25
53
1
2 |  | 15-janv-21 |  |  | 123479 | 175852 | FCIU7615218 | MONTREAL EXPRESS | 2021-01-21 | 2021-02-02
3 |  | 22-janv-21 |  |  | 123480 | 175853 | FFAU1234958 | QUEBEC EXPRESS | 2021-01-28 | 2021-02-09
4 | 2 | 29-janv-21 |  | 241, 242 | 123481 | 175854 | HLBU3331389, UACU8476618 | OOCL MONTREAL | 2021-02-04 | 2021-02-16
5 | 2 | 2021-02-05 |  | 249, 250 | 123482 | 175855 | TCNU1860511, HLBU1404655 | TORONTO EXPRESS | 2021-02-11 | 2021-02-24
5 | 2 | 2021-02-04 |  | 251, 222 | 123483 | 175856 | SUDU8604541 | MAERSK PENANG | 2021-02-10 | 2021-02-22
6 | 2 | 2021-02-12 |  | 252, 253 | 123484 | 175857 | CAIU4981508, TRKU4466656 | MONTREAL EXPRESS | 2021-02-18 | 2021-03-03
7 | 2 | 2021-02-19 |  | 254, 255 | 123485 | 175858 | TLLU8050982, HLBU2890504 | QUEBEC EXPRESS | 2021-02-26 | 2021-03-09
8 | 2 | 2021-02-26 |  | 256, 257 | 123486 | 175859 | HLBU3376655, HLBU1055609 | OOCL MONTREAL | 2021-03-04 | 2021-03-16
9 | 2 | 2021-03-05 |  | 258, 272 | 123487 | 175860 | MSCU5180832, TGBU7803252 | MSC CANBERRA - XA109A | 2021-03-10 | 2021-03-22
10 | 3 | 2021-03-12 |  | 273, 274, 275 | 123488 | 175861 | MRKU1066541, MRKU0285463, TCNU5689372 | EM KEA | 2021-03-24 | 2021-04-05
11 | 2 | 2021-03-19 |  | 276, 277 | 123489 | 175862 | HLBU1910859, UACU8603034 | QUEBEC EXPRESS | 2021-03-25 | 2021-04-06
12 | 2 | 2021-03-26 |  | 278, 279 | 123490 | 175863 | HLBU3306909, TCLU4426271 | OOCL MONTREAL | 2021-04-02 | 2021-04-15
13 | 1 | 2021-04-01 |  | 280 | 123491 | 175864 | BMOU6571858 | TORONTO EXPRESS 32W14 | 2021-04-08 | 2021-04-21
14 | 3 | 2021-04-09 |  | 281, 282, 283 | 123492 | 175865 | UACU5101876, CAIU4820308, UACU8262880 | MONTREAL EXPRESS | 2021-04-15 | 2021-04-27
15 | 2 | 2021-04-14 |  | 284, 285 | 123493 | 175866 | MRKU0461006, MRKU0447081 | EM KEA | 2021-04-21 | 2021-05-03
16 | 1 | 2021-04-23 |  | 286 | 123494 | 175867 | CAIU8531392 | OOCL MONTREAL | 2021-04-29 | 2021-05-11
17 | 2 | 2021-04-30 |  | 287, 288 | 123495 | 175868 | UACU8576710, GCXU5304734 | TORONTO EXPRESS | 2021-05-06 | 2021-05-18
18 | 2 | 2021-05-07 |  | 311, 312 | 123496 | 175869 | FANU1247115, TTNU5964564 | MONTREAL EXPRESS | 2021-05-17 | 2021-05-26
19 | 2 | 2021-05-14 |  | 313, 314 | 123497 | 175870 |  | QUEBEC EXPRESS | 2021-05-22 | 2021-06-01
20 |  | 2021-05-21 | [6 empty] | 2021-06-03 | 2021-06-15
21 | 2 | 2021-05-26 | 2021-05-26 | 315, 331 | 123498 | 175871 |  | CITY OF HONG KONG | 2021-06-03 | 2021-06-15
22 |  | 2021-06-04 | 2021-06-08 |  |  |  |  | MONTREAL EXPRESS | 2021-06-18 | 2021-06-29
23 | 2 | 2021-06-11 | 14-17 June | 332, 333 |  | 175872 |  | QUEBEC EXPRESS | 2021-06-24 | 2021-07-06
24 | 2 | 2021-06-18 |  | 334, 335 |  | 175873 |  | EM KEA | 2021-06-23 | 2021-07-05
25 | 2 | 2021-06-25 |  | 336, 337 |  | 175874 |  | MAERSK PATRAS | 2021-07-01 | 2021-07-13
26 | 2 | 2021-07-02 |  | 338, 339 |  | 175875 |  |  | 2021-07-08 | 2021-07-20
27 | 2 | 2021-07-09 |  | 351, 352 |  |  |  |  | 2021-07-15 | 2021-07-27
28 | 2 | 2021-07-16 |  | 353, 354 |  |  |  |  | 2021-07-22 | 2021-08-04